## Sheet1
|  | start | duration | end
Domain Knowledge Research | Understand Social and Public Health considerations of sidewalks | 2017-05-24 | 20 | 2017-06-13 | 42879
| Pedestrian Safety concerns | 2017-05-24 | 20 | 2017-06-13
| Persons with Physical Difficulties | 2017-05-24 | 20 | 2017-06-13
| Other Approaches to the Problem – Neighborhood Audits | 2017-05-24 | 20 | 2017-06-13
API/Technical Requirements | Python Image Processing Knowledge | 2017-06-03 | 20 | 2017-06-23
| Google/Bing Street View API Knowledge | 2017-06-03 | 10 | 2017-06-13
| Machine Learning/Neural Networks with Images | 2017-06-03 | 20 | 2017-06-23
| Best Practices for improving performance in image classification problems | 2017-06-03 | 20 | 2017-06-23
| GIS (Geographic Information System) file formats and interchanges | 2017-07-06 | 5 | 2017-07-11
Development of Machine Learning/Neural Network, Cross Validation, Testing
Image Sourcing and Labeling
| Google/Bing Image Collection with Geographic Data | 2017-06-14 | 1 | 2017-06-15
| Labeling of Images for Training and Test | 2017-06-15 | 10 | 2017-06-25
Model Development
| Development of Machine Learning/Neural Network, Cross Validation, Testing | 2017-06-15 | 75 | 2017-08-29
Documentation
| Written Paper - 1st Draft | 2017-06-01 | 34 | 2017-07-05
| Poster Creation | 2017-09-01 | 45 | 2017-10-16
| Poster Printing/Shipping | 2017-10-16 | 10 | 2017-10-26
Presentation/Review Steps
| Problem Proposal | 2017-05-24 | 7 | 2017-05-31
| Café Talk I | 2017-06-06 | 1 | 2017-06-07
| First Paper Draft Due | 2017-07-05 | 1 | 2017-07-06
| Café Talk II | 2017-07-11 | 1 | 2017-07-12
| Final Poster Presentation | 2017-11-09 | 1 | 2017-11-10
Formulas:
end = [start]+[duration]
start = [end, row above]